## Product Backlog
ID | Task
1 | As a customer I would like to be able to view other people's reviews so that I can see if the place is worth ordering from
4 | As a customer I would like to be able to track my order on the map so I know how far away my order is from arriving
5 | As a customer I want to be able to search for a menu item so that I can find easily what I might want to order. in Dynamic food-delivery website
6 | As a customer I want to view hyperlinks in basket webpage to so that I know where to go next.
7 | As a customer I want to be able to view 'help' section so that if I get stuck anywhere I can use this to guide me.
9 | As a customer I would like to view recommended popular items so that I can find whether it suits for me.
11 | As a customer I want to see symbols that show if a menu item is gluten free, vegan etc so that I can select it based on my preference.
12 | As a customer I want to be able to edit my profile so that the details of me kept are up to date.
13 | As a customer I would like to write review/s on menu item/s that I chose so that it can help others to decide whether to order it if they are not sure whether it is a good menu item.
14 | As a customer I want to view delivery time based on user Post Code so that I know when the order will approximately arrive.
15 | As a customer I want to view icons on basket webpage so that I know what actions need to be taken.
19 | As a customer I would like to view recommended popular items so that I can find out whether it suits for me.
20 | As a customer I want to get exclusive discount through Social Media so that I can benefit from cost.
21 | As a customer I want to see the restaurant food hygiene ratings so that I take this into consideration when I select menu item/s
22 | As a customer I want to be able to view all current deals and discounts so that I can take these into consideration when I select the menu item/s.
23 | As a customer I want to see images of the food on the menu so that I can select it based on how it looks like
24 | As a customer I want to see the restaurant opening and closing times so that I know when to order for menu item.
25 | As a customer I would like to create an account on the website so that I will be able to see deals and discounts of foods.
28 | As the owner, I want to allow/block users from ordering depending on the amount in the basket.
30 | as a customer, i want a full refund if theres a issue with my order
31 | As a onwer, I want to set time-limit on the website services e.g. blocking on restaurant closing times
32 | as a customer, I want to order without login/creating an account
33 | as the customer, I want to see which position my order is being done
34 | As the owner, I want to set a radius for where orders can be delivered to prevent users from placing undeliverable orders.
35 | As the owner, I want to be able to set when orders will be able to be taken.
36 | As the owner, I want to display order suggestions in the webpages e.g. burger display meal combo, or fries upgrade
37 | As the customer, I want to see nutritional values of my order e.g. protein and fat
38 | As a customer, I want to be to view previous orders made so that I can re-order the same meal or request a refund on the order.
39 | As the owner, I want the ability to add or remove items if they are not being sold anymore so that the website is kept up to date
40 | As the customer, I want to be able to give tips if I feel satisified with my order.

## Sprint Backlog & Burndown
Sprint Tasks |  |  | Days of the Sprint
Sprint 1 | Team Member | Story Points | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
quick recap on how write SQL statements | ALL | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
quick recap on how to code in PHP programming language related to database. | ALL | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
quick recap on GitLab | ALL | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
quick recap on JavaScript and HTML fundamentals | ALL | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
As part of database management team I would like to initialise a database so that I can allow users to use it for the project. | Leo | 10 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
As a customer I want to have a search bar for searching menu item so that I can find easily what I might want to order in Dynamic food-delivery website | Raphael | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 1 | 0 | 2
As a customer, I want to be able to have a form to make an account on the food delivery website. | Patrick | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
As a customer I want to be have a checkout form so that I can enter my details to pay for what I have ordered. | Kafui | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 1 | 1 | 1 | 1 | 0
As the owner, I want to have a toggle button block certain items from being bought e.g. if they not on stock | ALL | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
As a customer I want to have a basket page so that I can see what I have added to my order. | Ryan | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1
As a customer I want to be able to customise food items so that I can ensure the food is allergy friendly. | Patrick | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 1 | 0 | 1 | 0 | 0
| Total | 54 | 52.5 | 50.5 | 48.5 | 47.5 | 47.5 | 47.5 | 47.5 | 46 | 42.5 | 38.5 | 36.5 | 34.5 | 31.5 | 26.5 | 25.5 | 22.5 | 20.5 | 19.5 | 16.5 | 14.5 | 11
Students should record how many velocity points they worked on a task or how many are remaining for each task; they should then update the total as well. The total row would reach to zero when all tasks are completed.

## Sprint Review
Sprint Review
For Sprint 1, We created forms for the pages specified in the sprint backlog such as a search bar, a checkout form, basket page and account creation forms. We did encounter issues with regards to initialising the database. However, we have contacted the sys helpdesk to help resolve this issue. Another issue we had was when we had created epic stories but, now they have been edited to smaller ones. We decided to postpone implementing the feature of customising the food items as we had thought later that you must fully implement the most basic and vital features of the website before we include the special features. Using GitLab, we were able to review each other's work to suggest what could be changed or added to complete the work.

## Sprint Retrospective
Sprint Retrospective
For Sprint 1, we used Microsoft teams and our private WhatsApp group to communicate with each other concerning issues we are having with the project and discuss work completed. We met once a week to briefly discuss what we have completed and issues we were having with the project and discuss what the focus should be in the next sprint. It is something that we have considered to continue doing. As a team, we have decided that rather than each of us focusing on each task that we picked we instead divide each task into subtasks and we select based on our comfort so that we would be able to fully implement it on time and have a flow in progress.