## Product Backlog
|  | Page | Dynamic | Notes
ID | Task
1 | As a customer I would like to be able to view other people's reviews so that I can see if the place is worth ordering from | Menu | static
4 | As a customer I would like to be able to track my order on the map so I know how far away my order is from arriving | Checkout | dynamic
5 | As a customer I want to be able to search for a menu item so that I can find easily what I might want to order. in Dynamic food-delivery website | Search | static
6 | As a customer, I want to be able have option to proceed from the basket to the checkout, menu and Home Page | basket | static
7 | As a customer I want to be able to view 'help' section so that if I get stuck anywhere I can use this to guide me. | Website Footer | static
9 | As a customer I would like to view recommended popular items so that I can find whether it suits for me. | Home | static
11 | As a customer I want to see symbols that show if a menu item is gluten free, vegan etc so that I can select it based on my preference. | Menu/Search | static
12 | As a customer I want to be able to edit my profile so that the details of me kept are up to date. | My account | dynamic
13 | As a customer I would like to write review/s on menu item/s that I chose so that it can help others to decide whether to order it if they are not sure whether it is a good menu item. | Contact Us | Dynamic
14 | As a customer I want to view delivery time based on user Post Code so that I know when the order will approximately arrive. | Checkout Page | Dynamic | Only In Me (show range
15 | As a customer I want to view icons on basket webpage so that I know what actions need to be taken. | Basket Page | dynamic | General Options (salad)
20 | As a customer I want to get exclusive discount through Social Media so that I can benefit from cost. | Social Page | Dynamic | Take out % of total
21 | As a customer I want to see the restaurant overall ratings so that I take this into consideration when I select menu item/s | Footer | Static
22 | As a customer I want to be able to view all current deals and discounts so that I can take these into consideration when I select the menu item/s. | Offers | Dynamic | Above Mains on index page
23 | As a customer I want to see images of the food on the menu so that I can select it based on how it looks like | menu | static
24 | As a customer I want to see the restaurant opening and closing times so that I know when to order for menu item. | Footer | Static
25 | As a customer I would like to create an account on the website so that I will be able to see deals and discounts of foods. | Account Page | Dynamic
28 | As the owner, I want to allow/block users from ordering depending on the amount in the basket. | Basket Page |  | Do to in Sprint 3
30 | as a customer, i want a full refund if theres a issue with my order | Contact Us Page | static | Do do in Sprint 3
31 | As a onwer, I want to set time-limit on the website services e.g. blocking on restaurant closing times | Contact Us Page | static
32 | as a customer, I want to order without login/creating an account | Checkout Page | static
33 | as the customer, I want to see which position my order is being done | Checkout Page | dynamic | Increment +1 after order 3.
34 | As the owner, I want to set a radius for where orders can be delivered to prevent users from placing undeliverable orders. | Checkout Page | Static | If outside ME display outside cant show
36 | As the owner, I want to display order suggestions in the webpages e.g. burger display meal combo, or fries upgrade |  |  | If a side is not selected, show this option (note)
37 | As the customer, I want to see nutritional values of my order e.g. protein and fat | Menu/Search page | Static | Just Cal, Gluten Free, Spicy
38 | As a customer, I want to be to view previous orders made so that I can re-order the same meal | Account Page | dynamic | Just increment order
40 | As the customer, I want to be able to give tips if I feel satisified with my order. | Checkout Page | Static | Pop up notification on browser.
41 | If you are login, sends to checkout | Basket Area | dynamic | Create a 2nd checkout page for this . Do in Sprint 3
40 | As the customer, I want to be able to give tips if I feel satisified with my order. | Checkout Page | Static | Pop up notification on browser.
41 | If you are login, sends to checkout | Basket Area | dynamic | Create a 2nd checkout page for this . Do in Sprint 3
42

## Sprint Backlog & Burndown
| Sprint Tasks |  |  | Days of the Sprint
| Sprint 2 | Team Member | Story Points | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | As a costumer I want a well design home page to start my web experience with this restaurant | Leo | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | As a customer I would like to create an account on the website so that I will be able to see deals and discounts of foods. | Patrick | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | As a costumer I want to search the food items | Raphael | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | As a customer, I want to be able have option to proceed from the basket to the checkout, menu and Home Page | Ryan | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | As a costumer, I want to know that my order is ready to be deliver (after the checkout page) | Kafui | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | As a owner, I want to limit my order range only for my local area (checkout) | Leo | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | As a owner, I want to add a minimum order size for delivery | Ryan | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | As a customer, If I am already login-in I want to proceed to checkout, without inputing my details in. | Patrick | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | As a customer,I want to view all avaliable food range on the Menu Page | Raphael | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | As the customer, I want to be able to give tips if I feel satisified with my order. | Kafui | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | As a customer, I want a FAQ/Help Section if I need help before and during while visiting the website | Ryan (ALL) | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85
Ask Surgey about this page.
Students should record how many velocity points they worked on a task or how many are remaining for each task; they should then update the total as well. The total row would reach to zero when all tasks are completed.
Notes:
Instead of print while search, is to print the whole table (9)

## Sprint Review
Sprint Review
For Sprint 1, We created forms for the pages specified in the sprint backlog such as a search bar, a checkout form, basket page and account creation forms. We did encounter issues with regards to initialising the database. However, we have contacted the sys helpdesk to help resolve this issue. Another issue we had was when we had created epic stories but, now they have been edited to smaller ones. We decided to postpone implementing the feature of customising the food items as we had thought later that you must fully implement the most basic and vital features of the website before we include the special features. Using GitLab, we were able to review each other's work to suggest what could be changed or added to complete the work.

## Sprint Retrospective
Sprint Retrospective
For Sprint 1, we used Microsoft teams and our private WhatsApp group to communicate with each other concerning issues we are having with the project and discuss work completed. We met once a week to briefly discuss what we have completed and issues we were having with the project and discuss what the focus should be in the next sprint. It is something that we have considered to continue doing. As a team, we have decided that rather than each of us focusing on each task that we picked we instead divide each task into subtasks and we select based on our comfort so that we would be able to fully implement it on time and have a flow in progress.