## Product Backlog
ID | Task
1 | As a customer I would like to be able to view other people's reviews so that I can see if the place is worth ordering from
2 | As a customer I would like to be able to track my order on the map so I know how far away my order is from arriving
3 | As a customer I want to view hyperlinks in basket webpage to so that I know where to go next.
4 | As a customer I want to be able to view 'help' section so that if I get stuck anywhere I can use this to guide me.
5 | As a customer I would like to view recommended popular items so that I can find whether it suits for me.
6 | As a customer I want to see symbols that show if a menu item is gluten free, vegan etc so that I can select it based on my preference.
7 | As a customer I want to be able to edit my profile so that the details of me kept are up to date.
8 | As a customer I would like to write review/s on menu item/s that I chose so that it can help others to decide whether to order it if they are not sure whether it is a good menu item.
9 | As a customer I want to view delivery time based on user Post Code so that I know when the order will approximately arrive.
10 | As a customer I want to view icons on basket webpage so that I know what actions need to be taken.
11 | As a customer I would like to view recommended popular items so that I can find out whether it suits for me.
12 | As a customer I want to get exclusive discount through Social Media so that I can benefit from cost.
13 | As a customer I want to see the restaurant food hygiene ratings so that I take this into consideration when I select menu item/s
14 | As a customer I want to be able to view all current deals and discounts so that I can take these into consideration when I select the menu item/s.
15 | As a customer I want to see images of the food on the menu so that I can select it based on how it looks like
16 | As a customer I want to see the restaurant opening and closing times so that I know when to order for menu item.
17 | As the owner, I want to allow/block users from ordering depending on the amount in the basket.
18 | as a customer, i want a full refund if theres a issue with my order
19 | As a owner, I want to set time-limit on the website services e.g. blocking on restaurant closing times
20 | as a customer, I want to order without login/creating an account
21 | as the customer, I want to see which position my order is being done
22 | As the owner, I want to set a radius for where orders can be delivered to prevent users from placing undeliverable orders.
23 | As the owner, I want to be able to set when orders will be able to be taken.
24 | As the owner, I want to display order suggestions in the webpages e.g. burger display meal combo, or fries upgrade
25 | As the customer, I want to see nutritional values of my order e.g. protein and fat
26 | As a customer, I want to be to view previous orders made so that I can re-order the same meal or request a refund on the order.
27 | As the owner, I want the ability to add or remove items if they are not being sold anymore so that the website is kept up to date

## Sprint Backlog & Burndown
Sprint Tasks |  |  | Days of the Sprint
Sprint 2 | Team Member | Story Points | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
As a costumer I want a well design home page to start my web experience with this restaurant | Leo | 5 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
As a customer I would like to create an account on the website | Patrick | 8 | 0 | 0 | 0 | 0.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
As a costumer I want to search the food items | Raphael | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
As a customer, I want to be able have option to proceed from the basket to the checkout, menu and Home Page | Ryan | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
As a costumer, I want to know that my order is ready to be deliver (after the checkout page) | Kafui | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
As a owner, I want to limit my order range only for my local area (checkout) | Leo | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
As a owner, I want to add a minimum order size for delivery | Ryan | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
As a customer, If I am already login-in I want to proceed to checkout, without inputing my details in. | Patrick | 8 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
As a customer,I want to view all avaliable food range on the Menu Page | Raphael | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
As the customer, I want to be able to give tips if I feel satisified with my order. | Kafui | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
As the customer I want to be able to have a FAQ webpage that helps me during the website experience | Kafui, Ryan, Leo, Patrick,Raphael | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 65 | 65 | 65 | 65 | 63.5 | 60.5 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60
Key: |  |  | Days of the Sprint 1: Students should record how many velocity points they worked on a task or how many are remaining for each task; they should then update the total as well. The total row would reach to zero when all tasks are completed.
Green - New tasks for this sprint

## Sprint Review
Sprint Review

## Sprint Retrospective
Sprint Retrospective